## Parthasarathy S (Lead)
Iteration (Day) | Date | Feature / Change | Description | Start Time | End Time | Time Taken | Extra / Overtime Time (From–To) | Extra Hours | Total Day Hours | Carried Forward to Next Day | Status
1 | 2026-06-17 | • Docker Build Fix (Cross-Platform Setup) | Fixed Docker image build failures by switching to CPU-only PyTorch, adding the missing libgl1 system library, and correcting the Redis service hostname, so the app builds and starts cleanly in containers. | 10:00 AM | 12:15 PM | 2h | — | — | 8h | No | Completed
|  | • Security: Remove Secrets from Repo | Removed hard-coded secrets from .env.example and added backend/.env to .gitignore, so credentials can no longer be committed by accident. | 12:15 PM | 1:45 PM | 1h |  |  |  | No | Completed
|  | • Enterprise Chunker + Image Vision Pipeline (Initial Build) | Added the first version of the smarter document chunker and the image/vision processing pipeline (document model, orchestrator stage, synthesis URL fix); removed the old page-count limit on PDF uploads. | 1:45 PM | 7:00 PM | 5h |  |  |  | Yes | In Progress
2 | 2026-06-18 | • Windows Dev Environment End-to-End Fix | Fixed the full ingestion pipeline on a Windows machine: Docling parser, Celery worker pool mode, BGE embedding model isolation, database keep-alive settings, and the Gemma endpoint URL, so the app runs start to finish on Windows. | 10:00 AM | 12:32 PM | 2h 17m | — | — | 8h | No | Completed
|  | • Reranker Download Reliability Fix | Disabled Hugging Face's Xet CDN and raised the model download timeout so the BGE reranker model downloads reliably instead of failing or hanging. | 12:32 PM | 3:19 PM | 2h 17m |  |  |  | No | Completed
|  | • Frontend API Proxy — Fix CORS Errors | Routed frontend API calls through the Next.js proxy instead of calling the backend directly, eliminating CORS errors in the browser. | 3:19 PM | 4:43 PM | 1h 9m |  |  |  | No | Completed
|  | • Chunk Viewer Proxy Fix | Fixed the Chunk Viewer UI to fetch through the Next.js proxy rather than a hard-coded localhost:8000 URL, so it also works outside local dev. | 4:43 PM | 5:51 PM | 1h 9m |  |  |  | No | Completed
|  | • Query Latency Optimization | Cut end-to-end query response time from roughly 30 seconds to about 4 seconds by warming up (pre-loading) the ML models at server startup instead of on the first request. | 5:51 PM | 7:00 PM | 1h 9m |  |  |  | No | Completed
3 | 2026-06-19 | • Phase 1: Multimodal Extraction & Image Store | Built the full image/table extraction pipeline: pulls figures and tables out of PDFs, generates AI captions and OCR text via Gemma vision, stores them in a new image_store table, uploads to a private Supabase bucket with signed URLs, and surfaces them as citations in query answers. | 10:00 AM | 2:18 PM | 3h 33m | — | — | 8h | No | Completed
|  | • Table Crop Image Storage (Groundwork) | Extended the image store migration so table screenshots (crops) can also be uploaded and linked back to their table_store rows via an image_storage_path field. | 2:18 PM | 2:54 PM | 0h 36m |  |  |  | No | Completed
|  | • Phase 2: Retrieval Accuracy (Intent Routing + Fusion) | Added a query-intent classifier (Gemma-backed with a rule-based fallback), a 'balanced pool' search step that pulls fairly from every store, and reciprocal-rank-fusion re-ranking, so answers draw from the right document stores instead of one type dominating. | 2:54 PM | 5:13 PM | 2h 4m |  |  |  | No | Completed
|  | • Phase 3: Source Citations & Page Traces | Citations now carry the exact source PDF path, storage bucket, and bounding box; clicking a citation opens the original PDF at the cited page, so every answer can be independently checked. | 5:13 PM | 6:42 PM | 1h 29m |  |  |  | No | Completed
|  | • Phase 4: Multi-PDF Graph — Design Spec | Wrote the design spec for connecting related facts across multiple PDFs using a Neo4j knowledge graph, with a safe degrade path if Neo4j is unavailable. | 6:42 PM | 7:00 PM | 0h 18m |  |  |  | Yes | In Progress
4 | 2026-06-22 | • Phase 4: Multi-PDF Knowledge Graph — Build | Implemented the Neo4j-backed graph that links related facts across different PDFs, falling back gracefully when Neo4j isn't reachable. | 10:00 AM | 2:45 PM | 4h | 10:00 PM – 11:19 PM | 1h 19m | 9h 19m | No | Completed
|  | • Image Store Bugfix — Stop Self-Wipe | Fixed a bug where the storing stage was deleting the image rows it had just written for the same document. | 2:45 PM | 5:00 PM | 2h |  |  |  | No | Completed
|  | • Legal Clause Extraction (Phase 2+3) | Added Gemma-driven extraction and enrichment of legal clauses — risk level, parties, and key dates — for legal documents. | 5:00 PM | 7:00 PM | 2h |  |  |  | No | Completed
5 | 2026-06-23 | • Chunked Page-by-Page Parser + Live Progress | Reworked the document parser to process PDFs page by page and stream progress to the UI in real time, instead of waiting for the whole document to finish. | 10:00 AM | 2:45 PM | 4h | — | — | 8h | No | Completed
|  | • One-Click Windows Startup Scripts | Added startup scripts and a run guide so the whole stack (API, worker, frontend) can be launched with a single click on Windows. | 2:45 PM | 7:00 PM | 4h |  |  |  | No | Completed
6 | 2026-06-29 | • OCR Engine + VLM Structured Extraction Pipeline | Added a dedicated OCR engine plus a vision-language-model pass that extracts structured data (not just captions) from document images. | 10:00 AM | 12:55 PM | 2h 40m | 10:00 PM – 10:37 PM | 0h 37m | 8h 37m | Yes | In Progress
|  | • Incremental Image Storage + Progressive UI + Adaptive OCR | Images now save as soon as each one is processed instead of waiting for the whole batch; the UI streams them into the panel live; OCR always runs when enabled so tables baked into scanned pages aren't lost; empty/false-positive 'tables' that were really chart images are filtered out. | 12:55 PM | 5:40 PM | 4h |  |  |  | Yes | In Progress
|  | • Config Defaults Hardening | Restored sane default values in the app config so a missing environment variable can no longer crash the Celery worker on startup. | 5:40 PM | 7:00 PM | 1h 20m |  |  |  | No | Completed
7 | 2026-06-30 | • Semantic Chunking + Cross-Store Image Routing | Switched chunking to a semantic (meaning-aware) strategy, made storage retry automatically on transient upload errors, and made cross-store image routing fully traceable — which store an image actually landed in — instead of guessed. | 10:00 AM | 2:45 PM | 4h | 10:00 PM – 11:37 PM | 1h 37m | 9h 37m | Yes | In Progress
|  | • Image Store Refactor — Pure Extraction Repository | Simplified image_store into a pure extraction repository (dropped embedding logic and a legacy flag) and made the stored_in field stay NULL until a row is actually routed somewhere, so status reporting is accurate. | 2:45 PM | 4:20 PM | 1h 20m |  |  |  | Yes | In Progress
|  | • DB Connection Pooler Reliability Fix | Fixed a connection-pooler bug by pinning the database search_path before registering the pgvector type, preventing intermittent vector-query failures. | 4:20 PM | 5:00 PM | 0h 40m |  |  |  | No | Completed
|  | • Store Router Column Fix | Fixed the store router silently dropping columns it had data for, and made table-crop writes atomic-safe so they can't collide with normal image routing. | 5:00 PM | 7:00 PM | 2h |  |  |  | No | Completed
8 | 2026-07-01 | • Pre-VLM Image Filter (Skip Junk Before VLM) | Added a production-grade filter that screens out junk images (icons, logos, blank regions) before they reach the expensive VLM call, plus an early icon detector that also skips a wasted OCR pass. | 10:00 AM | 11:00 AM | 1h | 10:00 PM – 11:37 PM | 1h 37m | 9h 37m | No | Completed
|  | • Chunking + VLM Performance & Safety Upgrade (A+B) | Switched chunking to a real token-accurate splitter, ran VLM image calls in parallel for roughly 3x speed, batched image embeddings, and gated semantic (LLM-based) chunking for safety; also surfaced the new image filter's metrics in the UI. | 11:00 AM | 12:45 PM | 1h 30m |  |  |  | No | Completed
|  | • VLM Table-Crop Reconstruction + Explicit Routing | Added VLM-based reconstruction of table crops so no image is silently dropped, then replaced a blunt heuristic with an explicit content classifier that makes the image-vs-table routing decision transparent and reviewable. | 12:45 PM | 4:30 PM | 3h |  |  |  | Yes | In Progress
|  | • Content Validation Stage + Quality Metadata | Added a validation stage that tags extraction-quality metadata on every document, merged in a teammate's multi-format PR, fixed a duplicated storage call that surfaced from that merge, and renumbered clashing database migration files. | 4:30 PM | 6:30 PM | 2h |  |  |  | No | Completed
|  | • Phase 3 Design: Stage 0 Document-Domain Profiling (RFC) | Wrote a design RFC for profiling each document's domain early in the pipeline to auto-tune image-filter thresholds. Documentation only — deferred, not implemented. | 6:30 PM | 7:00 PM | 0h 30m |  |  |  | No | Deferred / Not Started
9 | 2026-07-02 | • Image/Table Lineage Fix — stored_in Never NULL | Fixed image_store so every row gets a definite destination immediately (figures go to image_store, table crops go to table_store) instead of sitting in an ambiguous NULL state. | 10:00 AM | 10:44 AM | 0h 44m | 10:00 PM – 10:17 PM | 0h 17m | 8h 17m | No | Completed
|  | • Table-Store Enterprise Architecture (Slices 1-4) | Built the full image-to-table lineage system in four slices: a database schema linking images to the tables they came from, image-first processing order, a reconciliation gate that keeps Docling's numbers unless the VLM is provably more accurate, uniform table enrichment with no extra LLM calls, and hybrid metadata-filtered table search. | 10:44 AM | 3:50 PM | 4h 22m |  |  |  | No | Completed
|  | • Table-Store Reliability & Performance Fixes | Fixed lineage data loss, made merged-cell tables render faithfully, added multi-window retrieval for large tables, cleaned up performance bottlenecks, and fixed image_store tagging for images routed into table_store. | 3:50 PM | 5:33 PM | 1h 27m |  |  |  | Yes | In Progress
|  | • Chunk/Table Streaming UI Fix | Chunks and tables now stream into the UI while a document is still processing, with a final refetch once processing completes. | 5:33 PM | 6:16 PM | 0h 44m |  |  |  | No | Completed
|  | • Image Signed-URL Caching | Cached signed image URLs in-process so the UI polling loop stops hitting Supabase on every single poll, cutting unnecessary round trips. | 6:16 PM | 7:00 PM | 0h 44m |  |  |  | No | Completed
10 | 2026-07-03 | • Multi-Page Table Continuation + Structured Queries | Tables that span multiple PDF pages now stitch back together correctly, each cell tracks its own row/column span, the table store supports structured (non-freeform) queries, and the worker stamps which process produced each row. | 10:00 AM | 12:55 PM | 2h 40m | — | — | 8h | N/A (latest) | Completed
|  | • Table-Store Architecture Documentation | Wrote the full table-pipeline architecture document, plus interactive HTML views of the architecture for both executives and developers. | 12:55 PM | 7:00 PM | 5h 20m |  |  |  | N/A (latest) | Completed

## Ganesh
Iteration (Day) | Date | Feature / Change | Description | Start Time | End Time | Time Taken | Extra / Overtime Time (From–To) | Extra Hours | Total Day Hours | Carried Forward to Next Day | Status
1 | 2026-06-16 | • Repository initialized | Created the root folder structure with /backend (FastAPI), /frontend (Next.js 14), and docker-compose.yml so the entire stack runs with one command. | 10:00 AM | 11:54 AM | 1h 39m | — | — | 8h | No | Completed
|  | • Initial commit (bare scaffold) | The very first skeleton of code — empty FastAPI app and blank Next.js page — checked into GitHub to give the team a base to branch from. | 11:54 AM | 5:21 PM | 4h 43m |  |  |  | No | Completed
|  | • README with architecture overview | Documented the full system flow: PDF Upload → Docling parse → Gemma 4 26B AI router → BGE embeddings → 4 Supabase vector stores → Gemma synthesis → Answer with citations. | 5:21 PM | 7:00 PM | 1h 39m |  |  |  | Yes | In Progress
2 | 2026-06-17 | • Config fix — .env reading corrected | The app was failing to read environment variables (API keys, DB passwords) from the .env file. Fixed the config loader so all secrets are loaded correctly at startup. | 10:00 AM | 10:07 AM | 0h 7m | — | — | 8h | Yes | In Progress
|  | • SSL DB connection mode env variable | Added SSL_DB_CONN_MODE config flag so the database connection can enforce SSL encryption in production, preventing plain-text DB traffic. | 10:07 AM | 10:15 AM | 0h 7m |  |  |  | No | Completed
|  | • Supabase Storage integration (supabase_storage.py) | Built a dedicated service module (supabase_storage.py) that wraps the Supabase Storage SDK — acts as the 'file cabinet' module that knows how to save PDFs to and retrieve them from the cloud bucket. | 10:15 AM | 11:05 AM | 0h 51m |  |  |  | No | Completed
|  | • upload_file + download_file helpers | Two reusable functions: one to push any file to the Supabase rag-documents bucket, and one to pull it back down — used by the Celery AI worker when it processes a document. | 11:05 AM | 11:14 AM | 0h 9m |  |  |  | No | Completed
|  | • PDF saved to bucket; path recorded in document_registry | When a user uploads a PDF, it goes to the cloud bucket instead of the server disk. The cloud file path and bucket name are saved in the document_registry database table so the AI worker can locate it later. | 11:14 AM | 12:20 PM | 0h 51m |  |  |  | No | Completed
|  | • Celery worker downloads PDF from Supabase to temp file | The background AI worker (Celery) now downloads the PDF from Supabase into a local temporary file, processes it with the AI pipeline, then automatically deletes the temp file — keeping the server clean. | 12:20 PM | 12:28 PM | 0h 9m |  |  |  | No | Completed
|  | • Pipeline UI — delete, edit, details view | Added three UI actions to the pipeline management screen: delete a pipeline run, edit its metadata, and drill into stage-by-stage progress of any ingestion job. | 12:28 PM | 4:23 PM | 3h 10m |  |  |  | No | Completed
|  | • CLAUDE.md — AI agent context file | Added a documentation file that explains the entire codebase architecture, run commands, pipeline stages, and DB layer to AI coding assistants (Claude Code) so they can navigate the project without manual guidance. | 4:23 PM | 7:00 PM | 2h 37m |  |  |  | Yes | In Progress
3 | 2026-06-18 | • Celery worker retry logic | If the background AI worker fails mid-job (e.g. a network hiccup while downloading a PDF from Supabase), it now automatically retries instead of silently dropping the job. | 10:00 AM | 10:01 AM | 0h 1m | — | — | 8h | No | Completed
|  | • Celery run command corrected in docs | Fixed the documented command to start the Celery worker so all developers use the correct flags and queue name — preventing 'why isn't my worker picking up jobs?' confusion. | 10:01 AM | 10:27 AM | 0h 26m |  |  |  | No | Completed
|  | • Backend ingestion pipeline with batch processing | The core AI chain: Docling reads and OCR-extracts the PDF, Gemma 4 26B classifies the document type, BGE embeds the text chunks into 1024-dim vectors, and the result is written to the matching Supabase store — all happening in the background. | 10:27 AM | 10:59 AM | 0h 32m |  |  |  | Yes | In Progress
|  | • Docling → Gemma 4 router → BGE embed flow | The three-stage AI pipeline: (1) Docling reads text and tables from PDF pages, (2) Gemma 4 26B decides if the document is policy/financial/legal/research/entity, (3) BGE converts text into 1024-dimensional vectors for similarity search. | 10:59 AM | 11:03 AM | 0h 4m |  |  |  | No | Completed
|  | • 4 Supabase vector stores connected | Four specialized databases are wired up: vector_store (policy/entity), table_store (financial tables as JSON), clause_store (legal clauses with risk metadata), document_store (research chunks with citations). Each gets its own indexed data. | 11:03 AM | 11:12 AM | 0h 9m |  |  |  | Yes | In Progress
|  | • Celery + Redis async background worker | Document processing is offloaded to Celery (a task queue) backed by Redis (the message broker). Users see an instant job-accepted response; heavy AI processing runs separately in the background. | 11:12 AM | 11:16 AM | 0h 4m |  |  |  | No | Completed
|  | • Live ingestion_jobs stage tracking | A database table (ingestion_jobs) records the status of each pipeline stage (parsing → routing → chunking → embedding → storing). The frontend polls every 2 seconds to show a live progress bar. | 11:16 AM | 11:22 AM | 0h 5m |  |  |  | Yes | In Progress
|  | • REST API: POST /ingest + GET /ingest/status/{job_id} | Two API endpoints: POST to submit a PDF for processing (returns a job_id immediately), and GET to poll the live status of that job by its ID. | 11:22 AM | 11:26 AM | 0h 4m |  |  |  | No | Completed
|  | • Upload page /upload (drag-and-drop) | A clean drag-and-drop file upload page in the Next.js frontend where users pick a PDF, choose the document type (policy/financial/legal/etc.), and submit it to the AI ingestion pipeline. | 11:26 AM | 11:45 AM | 0h 4m |  |  |  | No | Completed
|  | • Query/chat page /query (initial version) | The first version of the Q&A interface where users type natural-language questions and receive AI-generated answers with source citations. | 11:45 AM | 11:54 AM | 0h 9m |  |  |  | Yes | In Progress
|  | • Typed API client + custom React hooks | A typed TypeScript API client and custom React hooks (e.g. useIngestionPipeline) that abstract all backend HTTP calls, keeping UI components clean and decoupled from networking logic. | 11:54 AM | 11:59 AM | 0h 4m |  |  |  | No | Completed
|  | • Next.js proxy — CORS fix for all API calls | All frontend API calls are routed through a Next.js server-side proxy instead of calling FastAPI directly. This eliminates browser CORS errors in both development and production. | 11:59 AM | 12:00 PM | 0h 2m |  |  |  | No | Completed
|  | • graphify description added to CLAUDE.md | Documented the graphify code-graph tool in CLAUDE.md so AI coding assistants can instantly navigate cross-file relationships (call graphs, imports, AST nodes) in the codebase. | 12:00 PM | 12:02 PM | 0h 2m |  |  |  | No | Completed
|  | • Dark theme + toggle button on Documents page | Introduced a dark colour scheme to the Documents page with a theme toggle button — lets users switch between light and dark modes with one click. | 12:02 PM | 12:14 PM | 0h 12m |  |  |  | No | Completed
|  | • Progress card redesign — per-stage granular status | The ingestion job progress card was rebuilt to show individual stage statuses (e.g. 'Parsing 60% · Embedding 0%') with estimated percentages instead of a single generic spinner. | 12:14 PM | 6:51 PM | 5h 52m |  |  |  | Yes | In Progress
|  | • Query latency: ~30s → ~4s (model warm-up at startup) | BGE and Gemma reranker models were loaded from disk on every query request (cold start). Changed to load them once at server startup (warm start), reducing per-query AI time by ~87%. | 6:51 PM | 7:00 PM | 0h 9m |  |  |  | No | Completed
4 | 2026-06-19 | • API connection reload behavior fixed | The frontend API client was not correctly re-initializing after a browser page refresh, causing silent failures. Fixed the initialization lifecycle so it reliably reconnects. | 10:00 AM | 10:01 AM | 0h 1m | — | — | 8h | No | Completed
|  | • Backend run command corrected in docs | Fixed the uvicorn startup command in the README and CLAUDE.md to use the correct module path (app.main:app) so developers don't hit import errors on first run. | 10:01 AM | 10:20 AM | 0h 18m |  |  |  | No | Completed
|  | • image_store DB table + migration SQL | A new database table (image_store) was created with a schema migration. It stores per-image metadata: cloud file path, AI-generated caption, OCR text, 1024-dim embedding vector, and the source document it came from. | 10:20 AM | 10:44 AM | 0h 25m |  |  |  | No | Completed
|  | • ExtractedImage Python data model | A Python dataclass that represents a single extracted image as it flows through the pipeline — carries caption, OCR text, storage path, bounding box coordinates, and page number. | 10:44 AM | 11:03 AM | 0h 18m |  |  |  | No | Completed
|  | • table_store.image_storage_path column added | Extended the existing table_store database table with a new column to save the Supabase Storage path of the corresponding table screenshot, so financial tables can be retrieved as images too. | 11:03 AM | 11:21 AM | 0h 18m |  |  |  | No | Completed
|  | • Docling extracts figures + table crops from PDFs | Used Docling's generate_picture_images API to pull out embedded figures (charts, diagrams) and screenshot crops of table regions from PDF pages as individual image files. | 11:21 AM | 12:13 PM | 0h 37m |  |  |  | Yes | In Progress
|  | • Gemma vision describe_image — caption + OCR per image | For each extracted image, the Gemma 4 26B Vision Language Model (VLM) is called to produce: (1) a natural-language description of what the image shows, and (2) OCR text of any text visible inside the image. | 12:13 PM | 12:50 PM | 0h 37m |  |  |  | Yes | In Progress
|  | • Signed URL helper for private Supabase bucket | A utility function that generates time-limited, signed access URLs for images stored in Supabase's private bucket — the frontend can display images securely without ever exposing bucket credentials. | 12:50 PM | 1:44 PM | 0h 25m |  |  |  | No | Completed
|  | • image_store repository + store_images service | A repository layer (image_store_repository.py) and a storage service function (store_images) that handle inserting image records and their embedding vectors into the database after the VLM stage. | 1:44 PM | 2:03 PM | 0h 18m |  |  |  | No | Completed
|  | • Retrieval extended to query image_store | The vector search retrieval pipeline was extended to also search image_store during queries. Results include image-specific fields (caption, signed URL, page) alongside regular text chunks. | 2:03 PM | 2:21 PM | 0h 18m |  |  |  | No | Completed
|  | • Image citations with signed URLs in query responses | When the AI generates an answer, any relevant images are included in the citations panel as signed-URL previews — users can view the actual chart or table from the source document inline. | 2:21 PM | 2:58 PM | 0h 37m |  |  |  | Yes | In Progress
|  | • Full orchestrator images stage pipeline | The ingestion orchestrator gained a dedicated 'Images' stage that runs the complete pipeline for every image in a document: extract → Gemma caption/OCR → upload to bucket → embed → write to image_store. | 2:58 PM | 3:22 PM | 0h 25m |  |  |  | No | Completed
|  | • Table crop screenshots uploaded to Supabase | Table screenshot crops extracted by Docling are uploaded to Supabase Storage and the cloud path is saved in table_store.image_storage_path for later retrieval alongside the table's text data. | 3:22 PM | 3:41 PM | 0h 18m |  |  |  | No | Completed
|  | • Query intent classifier (Gemma + keyword fallback) | Before searching the database, the system now classifies the user's question into a type: policy, financial, legal, research, or entity. Gemma 4 26B is the primary classifier; keyword rules serve as a safe fallback if the model is unavailable. | 3:41 PM | 4:33 PM | 0h 37m |  |  |  | No | Completed
|  | • Balanced pool + RRF cross-store result fusion | When multiple vector stores are searched, results are merged using Reciprocal Rank Fusion (RRF) — a proven algorithm that fairly combines ranked lists from different sources without artificially favouring any one store. | 4:33 PM | 5:10 PM | 0h 37m |  |  |  | No | Completed
|  | • Rerank candidate pool increased: 12 → 40 | The CrossEncoder re-ranker model now considers up to 40 candidate text chunks instead of 12, giving it a much larger pool to identify the most relevant context before passing to Gemma for synthesis. | 5:10 PM | 5:46 PM | 0h 37m |  |  |  | No | Completed
|  | • Retriever uses intent to select target stores | The retrieve() function now receives the intent classification result and selects only the matching stores to query — e.g. a 'legal' query only searches clause_store, a 'financial' query only table_store. | 5:46 PM | 6:23 PM | 0h 37m |  |  |  | No | Completed
|  | • Phase 2 retrieval spec documented in docs/ | A technical specification document was written in docs/ describing the Phase 2 retrieval design — intent routing, balanced pool, and cross-encoder fusion — for team alignment and future reference. | 6:23 PM | 7:00 PM | 0h 37m |  |  |  | No | Completed
5 | 2026-06-22 | • Bug fix: image rows no longer wiped on re-run | Running the Images ingestion stage twice was deleting previously stored image_store rows. Fixed to be idempotent — re-runs only add/update records, never wipe existing ones. | 10:00 AM | 7:00 PM | 8h | — | — | 8h | No | Completed (Hotfix)
6 | 2026-06-23 | • run.bat — one-click full-stack startup | A Windows batch script that starts Redis, the FastAPI backend, the Celery background AI worker, and the Next.js frontend in the correct dependency order — all from a single double-click. | 10:00 AM | 1:57 PM | 3h 12m | — | — | 8h | No | Completed
|  | • setup.bat — first-time dependency installer | A one-time setup script for new developers: creates Python virtual environments, installs pip and npm dependencies, and verifies Docker is available before the team tries to run the app. | 1:57 PM | 3:33 PM | 1h 36m |  |  |  | No | Completed
|  | • stop.bat — graceful service shutdown | Cleanly terminates all running services (FastAPI, Celery, Redis, Next.js) without leaving orphaned background processes that consume memory. | 3:33 PM | 5:24 PM | 1h 36m |  |  |  | No | Completed
|  | • RUN.md — Windows startup guide | A step-by-step Markdown guide for Windows developers covering prerequisites (Docker, Python, Node), environment setup, and how to use the three batch scripts. | 5:24 PM | 7:00 PM | 1h 36m |  |  |  | No | Completed
7 | 2026-06-25 | • Multi-store routing bug fix | A routing logic bug caused all documents to be stored in vector_store regardless of type. Fixed: policy docs → vector_store, financial → table_store, legal → clause_store, research → document_store. | 10:00 AM | 10:35 AM | 0h 35m | — | — | 8h | No | Completed
|  | • Chat response speed improved | Reduced round-trip query latency by optimising how retrieved text chunks are serialised and passed to the Gemma 4 synthesis model — less redundant data processing per request. | 10:35 AM | 5:49 PM | 6h 14m |  |  |  | Yes | In Progress
|  | • Citation panel redesign (full source metadata) | Each AI response now shows a collapsible citations panel with: source filename, page number, store type (e.g. clause_store), relevance % score, and the full raw chunk text so users can verify answers against the source. | 5:49 PM | 7:00 PM | 1h 11m |  |  |  | Yes | In Progress
8 | 2026-06-26 | • Image citations rendering in chat panel | After the image pipeline from Iteration 4 was built, citations now also display images — a relevant chart or table crop from the source PDF is shown inline in the citations panel. | 10:00 AM | 11:56 AM | 1h 41m | — | — | 8h | No | Completed
|  | • Recent chats sidebar added | A sidebar panel was added to the Query page listing the user's past conversation sessions by title and timestamp. Clicking a past session restores the full conversation thread. | 11:56 AM | 2:17 PM | 1h 51m |  |  |  | Yes | In Progress
|  | • Query page full UI overhaul | Major redesign of the /query page: animated typing indicator while the AI is thinking, document-type filter chips to scope which stores are searched, suggested starter questions for new users, and a Clear Conversation button. | 2:17 PM | 4:23 PM | 1h 51m |  |  |  | No | Completed
|  | • Image OCR graceful error handling | When OCR processing fails for a particular image (blurry scan, unsupported format), the pipeline previously crashed the entire ingestion job. Now it gracefully skips the bad image, logs the error, and continues with the rest. | 4:23 PM | 6:55 PM | 2h 32m |  |  |  | Yes | In Progress
|  | • Recent chats state refresh bug fixed | A React state management bug where the recent chats sidebar didn't refresh after a new conversation was created. Fixed by correcting the state update trigger in the component lifecycle. | 6:55 PM | 7:00 PM | 0h 5m |  |  |  | No | Completed
9 | 2026-06-29 | • Document delete cascades across all 5 stores | Previously, deleting a document from document_registry left orphaned rows in vector_store, table_store, clause_store, document_store, and image_store. Added cascade delete logic to clean all 5 tables atomically. | 10:00 AM | 11:54 AM | 1h 39m | — | — | 8h | No | Completed
|  | • Gemma process flow displayed in chat response | The chat response panel now includes a collapsible 'Process' section showing the internal reasoning steps and retrieval path Gemma used — useful for debugging and building user trust in the AI's answers. | 11:54 AM | 2:10 PM | 1h 46m |  |  |  | No | Completed
|  | • Gemma 4 synthesis latency further reduced | Tuned the prompt format and inference parameters for the Gemma 4 26B synthesis call to reduce unnecessary token generation — fewer tokens in the prompt = lower latency on the CDAC inference server. | 2:10 PM | 3:34 PM | 1h 25m |  |  |  | No | Completed
|  | • miniLM reranker replaces bge-reranker-large | Swapped the heavy BAAI/bge-reranker-large CrossEncoder model with a lighter miniLM-based reranker. Significantly faster inference with comparable ranking accuracy for this domain's typical query lengths. | 3:34 PM | 5:35 PM | 1h 46m |  |  |  | No | Completed
|  | • Config hardened — missing .env keys no longer crash worker | If any optional .env variable is absent (e.g. RERANKER_MODEL), the config module now falls back to a sensible default rather than throwing a KeyError that would kill the Celery worker process on startup. | 5:35 PM | 7:00 PM | 1h 25m |  |  |  | No | Completed
10 | 2026-06-30 | • Chat UI shows model name in every response | A label is shown below each AI answer (e.g. 'Generated by Gemma 4 26B') so users and developers always know which AI model produced the response — especially important when fallback models are active. | 10:00 AM | 10:56 AM | 0h 56m | — | — | 8h | No | Completed
|  | • Confidence score corrected (logits → sigmoid → 0–100%) | The confidence score displayed in the UI was using raw CrossEncoder logits, which are not bounded or meaningful to users. Fixed to apply a sigmoid function to convert raw scores into a proper 0–100% relevance percentage. | 10:56 AM | 7:00 PM | 7h 4m |  |  |  | No | Completed
11 | 2026-07-01 | • Correction of Routing in the Database stores | Fixed the Knowledge store by modifying the chunk storage logic to ensure all data is properly considered during ingestion and retrieval, resolving incomplete indexing issues. Additionally, analyzed the image_store table to identify routing inconsistencies and prepared a detailed implementation plan to correctly categorize and migrate images to their appropriate destinations (image_store, table_store, or vector_store) based on content_class and extraction_quality metadata. | 10:00 AM | 7:00 PM | 8h | — | — | 8h | No | Completed

## Murali
Iteration (Day) | Date | Feature / Change | Description | Start Time | End Time | Time Taken | Extra / Overtime Time (From–To) | Extra Hours | Total Day Hours | Carried Forward to Next Day | Status
1 | 2026-06-17 | • Upload page redesign and pipeline upload setup | Reworked the upload screen to match the provided PPT design, added upload flow wiring, taxonomy support, API client updates, and backend pipeline run handling needed for document ingestion. | 10:00 AM | 2:45 PM | 4h | — | — | 8h | Yes | Completed
|  | • Upload field UI fixes | Corrected upload form field behavior and aligned related database migration and connection pieces with the updated upload experience. | 2:45 PM | 7:00 PM | 4h |  |  |  | No | Completed
2 | 2026-06-18 | • .gitignore cleanup | Updated ignore rules to keep unnecessary and generated files out of version control. | 10:00 AM | 2:45 PM | 4h | — | — | 8h | No | Completed
|  | • Documents module UI upgrade and dark theme toggle | Improved the Documents pages and related screens, introduced theme switching, updated layout, header, and sidebar behavior, and refreshed upload, query, and document screens. | 2:45 PM | 7:00 PM | 4h |  |  |  | Yes | Completed
3 | 2026-06-19 | • Additional UI polish across documents, upload, and query screens | Follow-up styling and layout adjustments across document list, upload page, query page, and global styling after the main theme and UI update. | 10:00 AM | 7:00 PM | 8h | — | — | 8h | No | Completed
4 | 2026-06-22 | • Query, header, and upload UI fixes | Fixed visible UI issues in the query page, header, and file dropzone to improve page layout and upload interaction. | 10:00 AM | 7:00 PM | 8h | — | — | 8h | No | Completed
5 | 2026-06-23 | • Content-based multi-store routing and lossless image extraction | Added smarter RAG routing so content can be directed to the right storage and retrieval path, while preserving extracted images more accurately for downstream querying and synthesis. | 10:00 AM | 7:00 PM | 8h | — | — | 8h | No | Completed
6 | 2026-06-24 | • Recent chats feature and query page enhancements | Added chat session support, backend chat APIs and migration, frontend query page updates, and recent chats handling so users can revisit prior conversations. | 10:00 AM | 7:00 PM | 8h | — | — | 8h | No | Completed
7 | 2026-06-25 | • Chat window UI fix | Cleaned up the chat window presentation and related styling and interaction issues in the query experience. | 10:00 AM | 7:00 PM | 8h | — | — | 8h | No | Completed
8 | 2026-06-26 | • Image processing and upload overwrite improvements | Improved image and document detail display, strengthened ingestion error logging, and allowed uploaded files to be overwritten when needed. | 10:00 AM | 7:00 PM | 8h | — | — | 8h | No | Completed
9 | 2026-06-29 | • Light-mode polish, session reset handling, and collapsible sidebar updates | Improved light-theme elevation styles, added session reset behavior in chat, and streamlined sidebar and theme toggle interactions for a cleaner UI. | 10:00 AM | 2:45 PM | 4h | — | — | 8h | No | Completed
|  | • Sidebar branding enhancement | Added logo text and fade behavior for collapsed sidebar mode and adjusted button placement for better navigation clarity. | 2:45 PM | 7:00 PM | 4h |  |  |  | No | Completed
10 | 2026-06-30 | • Pipeline count badge, ingestion error handling, and markdown copy cleanup | Added a running pipeline count in the sidebar, improved ingestion error handling, and converted markdown output to plain text for cleaner copy behavior. | 10:00 AM | 7:00 PM | 8h | — | — | 8h | No | Completed
11 | 2026-07-01 | • Parse staging service for durable document processing | Built a durable parse-staging layer with database migrations, repositories, ingestion tasks, table chunk storage, graph and community services, and retrieval improvements to make document processing more reliable and resumable. | 10:00 AM | 2:45 PM | 4h | — | — | 8h | No | Completed
|  | • Multi-format ingestion and pagination recovery | Extended ingestion and parser behavior to support more document formats, recover pagination better, and added tests around table chunk handling for improved reliability. | 2:45 PM | 7:00 PM | 4h |  |  |  | No | Completed
12 | 2026-07-02 | • Fixed Document Parser, Supabase Storage and Testing | feat(document-parser): merge continuation tables for logical table reconstruction feat(supabase-storage): add retry logic for file downloads with error handling test(tests): add unit tests for staged ingestion pipeline and table merging functionality | 10:00 AM | 7:00 PM | 8h | — | — | 8h | No | Completed
13 | 2026-07-03 | • Fixed the Pipeline and Manual storage fix in the supabase | Fixed the pipeline when uploading documents. Fixed the ID view in the image store and table store. | 10:00 AM | 7:00 PM | 8h | — | — | 8h | No | Completed

## Notes & Methodology
Field | Explanation
Source | Generated from `git log` for author parthasarathys03 across all branches, project: rag-new-manthan (MANTHAN RAG system).
Layout | One row per feature/change. Iteration and Date columns are merged vertically across every feature shipped that day.
Standard Company Day | 10:00 AM – 7:00 PM (9h gross), minus a fixed 1h break (11:30-11:45 AM tea, 1:00-1:30 PM lunch, 4:00-4:15 PM tea) = 8 working hours/day net.
Start Time / End Time / Time Taken (per row) | The day's 8 working hours are split across that day's features, weighted by each feature's actual commit count that day (more commits on a feature = a larger, more realistic share of the day). Each feature is then placed sequentially into the 10-7 timetable, automatically skipping the three fixed break windows, giving each row a real clock-time slot. All rows for a day always sum to exactly 8h.
Extra / Overtime Time | Day-level (merged). Counted only from 10:00 PM onward, not 7:00 PM — the 7:00-10:00 PM window is travel + rest time after the office day ends, not work time. Shows the From-To range and duration actually worked past 10:00 PM, highlighted YELLOW. '—' = no overtime that day.
Total Day Hours | Day-level (merged) — 8h standard + Extra Hours (if any).
Carried Forward to Next Day | 'Yes' if this specific feature continued into the next iteration; 'No' if it was closed out the same day (usually via a merge commit).
Status | Per-feature: 'Completed', 'In Progress' (continues next iteration), or 'Deferred / Not Started' (design doc only, not built).
2026-07-03 note | Latest logged date at time of report — Carried Forward marked N/A since there is no next day of data yet. Its 8 working hours are split the same way as every other day.
Commit/push workflow note | Per user preference: commits and pushes for this project should be performed by Claude Code directly, keeping manual (developer-run) commits to a minimum.
Ganesh's sheet | Reproduced from his own submitted iteration log (MANTHAN_AI_RAG_ganeshe_DM_Iterations.xlsx), grouped by iteration exactly as he tracked it.
Murali's sheet | Reproduced from his own submitted work log (work_log.xlsx); 'Carried Forward' derived from status text ('...with later refinements' = Yes).
Team-wide format | Ganesh and Murali sheets now use the exact same 12-column table as Parthasarathy's sheet (Iteration, Date, Feature/Change, Description, Start/End Time, Time Taken, Extra/Overtime, Total Day Hours, Carried Forward, Status).
Ganesh/Murali overtime | Neither logged any work past standard office hours (10:00 AM - 7:00 PM), so Extra/Overtime Time is '—' and Total Day Hours is a flat 8h for every day on both their sheets.
Ganesh per-row timing basis | His own log's 'Time Taken' estimate per feature is used as a relative weight to split that day's 8 working hours (e.g. a ~1hr49min item gets a bigger slice than a ~13min one). Entries logged as spanning multiple days (e.g. '~7 days', 'same commit') use a small placeholder share since they don't represent single-day effort.
Murali per-row timing basis | His own log already states Time Taken per feature in whole hours per day, and those already sum to exactly 8h/day, so his stated hours are used directly to build the Start/End time slots.